## Start Here
Corrective Action Plan Template
Template purpose | Use this workbook to plan, assign, track, verify, and close corrective actions linked to a defect, nonconformance, customer complaint, NCR, SCAR, RCA, or 8D.
When to use it | Use it when an issue needs more than a simple task list: owners, due dates, evidence, verification, and an effectiveness check after implementation.
When a simpler list may be enough | A short action list may be enough for low-risk housekeeping items or one-off follow-up tasks that do not require evidence, verification, or customer response.
When to use a full 8D instead | Use a full 8D when the customer requires it, the issue is high risk, containment is complex, root cause needs formal analysis, or multiple disciplines need to work through D1-D8.
Suitability notice | General manufacturing quality use only. Adapt this template to your company, customer, product, process, and industry requirements. This template does not guarantee compliance with ISO 9001, IATF 16949, customer-specific requirements, or any audit standard. Not intended for medical device, pharma, FDA, Part 11, or validated regulated workflows. Ultimate determination of root cause, process compliance, and corrective action effectiveness remains the responsibility of the user.
Key terminology
Containment | Controls suspect product now so the customer or next process is protected while the cause is being investigated.
Correction | Fixes, sorts, reworks, replaces, or disposes of the affected product.
Corrective action | Addresses the confirmed cause so recurrence is reduced.
Preventive action | Reduces the chance of a similar issue occurring elsewhere, if applicable.
Verification | Checks that the action was completed as planned.
Effectiveness check | Checks whether the action worked over time, not just whether it was completed.
Closure | Formal confirmation that all actions are complete, evidence has been reviewed, effectiveness has been checked where required, and the issue owner has approved the CAP as closed. Closure is documented, not assumed.
Common mistakes to avoid
1. | Treating containment as corrective action.
2. | Closing actions without evidence.
3. | Assigning actions to departments instead of a named owner.
4. | Writing vague actions such as “review process”.
5. | Using “operator retrained” as the only action without addressing the process weakness.
6. | Forgetting the escape / detection failure.
7. | Not checking effectiveness after implementation.
8Dflow.com | Use this template when you need a clear corrective action plan for a standalone issue. When corrective actions are spread across many NCRs, SCARs, 8Ds, customer complaints, owners, due dates, evidence files, and customer updates, 8Dflow.com helps keep the work connected to the same quality issue.
Date format note | Use YYYY-MM-DD for date fields where possible. For combined owner/date cells, enter as: Name YYYY-MM-DD.
© 8Dflow.com For internal business use only. General manufacturing quality reference; adapt before use. No warranty is given as to accuracy, completeness, suitability, or compliance with any audit, regulatory, contractual, certification, or legal requirement. Do not redistribute, resell, or publish without 8Dflow’s written permission.
© 2026 8Dflow.com For internal adaptation only. Not for resale, republication, or redistribution as a standalone template without written permission.

## Corrective Action Plan
Corrective Action Plan
Complete the case header. | Add one row per action. | Keep containment, correction, corrective action, verification, and effectiveness separate. | Close only with evidence, not verbal confirmation. | Use YYYY-MM-DD dates.
Case header
Corrective Action Plan ID |  | Related RCA / NCR / SCAR / 8D / complaint |  | Customer |  | Supplier
Site / plant |  | Part / product |  | Part number / revision |  | Issue owner
Date opened |  | Target closure date |  | Customer response deadline |  | Overall status
Problem statement | Describe the issue in factual terms. Do not include assumed root cause. | Total suspect qty |  | Qty reworked / scrapped |  | Clean point / lot scope
Affected lot / batch |  | Quantity sorted |  | Quantity released |  | Disposition summary
Action tracker
Action ID | Reference ID (NCR/SCAR/Complaint) | Related issue / finding | Issue Type | Action type | Cause / escape point this action targets | Action proposed / implemented | Owner (person) | Department / function | Priority / risk | Proposed completion date | Actual completion date | Status | Evidence record ID / link | Verification method | Verification owner & date | Verification result | Effectiveness check required? | Effectiveness check due date | Effectiveness result | Closure date | Notes
© 8Dflow.com For internal business use only. General manufacturing quality reference; adapt before use. No warranty is given as to accuracy, completeness, suitability, or compliance with any audit, regulatory, contractual, certification, or legal requirement. Do not redistribute, resell, or publish without 8Dflow’s written permission.
© 2026 8Dflow.com For internal adaptation only. Not for resale, republication, or redistribution as a standalone template without written permission.

## Evidence Log
Evidence Log
Record proof that actions were completed or changed the process result. | Use Related Action ID to link evidence back to the tracker. | Use file name / link / location for photos, records, reports, and emails. | Do not rely only on verbal confirmation.
Evidence ID | Related Action ID | Evidence type | What the evidence shows | File name / link / location | Owner | Date added | Reviewed by | Supports closure? | Notes
© 8Dflow.com For internal business use only. General manufacturing quality reference; adapt before use. No warranty is given as to accuracy, completeness, suitability, or compliance with any audit, regulatory, contractual, certification, or legal requirement. Do not redistribute, resell, or publish without 8Dflow’s written permission.
© 2026 8Dflow.com For internal adaptation only. Not for resale, republication, or redistribution as a standalone template without written permission.

## Effectiveness Check
Effectiveness Check
Verification checks that an action was done. | Effectiveness checks whether the problem reduced, stopped, or stayed controlled. | Record sample size, time window, process reviewed, and acceptance criteria. | Link the check to an Evidence ID.
Effectiveness Check ID | Related Action ID | Related issue / root cause | Check method | Lot / quantity sample size checked | Time window tracked | Production area / process reviewed | Acceptance criteria | Result | Evidence ID / link | Further action needed? | Decision owner | Decision date | Notes
© 8Dflow.com For internal business use only. General manufacturing quality reference; adapt before use. No warranty is given as to accuracy, completeness, suitability, or compliance with any audit, regulatory, contractual, certification, or legal requirement. Do not redistribute, resell, or publish without 8Dflow’s written permission.

## Completed Example
| Completed Example — Returned stamped bracket with missing threadlocker | Returned stamped bracket with missing threadlocker
Use this as a practical example only. | Replace the scenario, actions, owners, dates, evidence, and acceptance criteria with your own issue details. | Keep occurrence-cause actions separate from escape / detection actions. | Close only after evidence and effectiveness are reviewed where required.
Example case header
Corrective Action Plan ID | CAP-2026-014 | Related RCA / NCR / SCAR / 8D / complaint | RCA-2026-014 / Complaint C-1842 | Customer | Northline Equipment | Supplier | Internal
Site / plant | Plant 2 | Part / product | Stamped mounting bracket | Part number / revision | BRK-4472 Rev C | Issue owner | M. Rivera
Date opened | 2026-06-04 | Target closure date | 2026-07-19 | Customer response deadline | 2026-06-18 | Overall status | Effectiveness check pending
Problem statement | Customer returned two stamped brackets from Lot L0626 with missing threadlocker on two fasteners. | Total suspect qty | 1500 | Qty reworked / scrapped | 12 reworked / 0 scrapped | Clean point / lot scope | Lot L0626 and WIP before pack station
Affected lot / batch | Lot L0626 | Quantity sorted | 1500 | Quantity released | After rework verification | Disposition summary | No shipment released before inspection
Example action tracker
Action ID | Reference ID (NCR/SCAR/Complaint) | Related issue / finding | Issue Type | Action type | Cause / escape point this action targets | Action proposed / implemented | Owner (person) | Department / function | Priority / risk | Proposed completion date | Actual completion date | Status | Evidence record ID / link | Verification method | Verification owner & date | Verification result | Effectiveness check required? | Effectiveness check due date | Effectiveness result | Closure date | Notes
A1 | Complaint C-1842 | Returned bracket missing threadlocker on two fasteners | Customer complaint | Containment | Suspect product from Lot L0626 before clean point | Quarantine finished goods and WIP from Lot L0626 until threadlocker presence is confirmed. | J. Nguyen | Production | Customer-critical | 2026-06-05 | 2026-06-05 | Verified | EV-001 | Inventory quarantine record reviewed | M. Rivera 2026-06-05 | Verified complete | No |  | Not due | 2026-06-05 | Containment completed before further shipment.
A2 | Complaint C-1842 | Returned bracket missing threadlocker on two fasteners | Customer complaint | Immediate correction / product rework | Affected finished goods may have missing threadlocker | Inspect 100% of finished goods and WIP from Lot L0626; apply controlled rework where missing threadlocker is found. | A. Patel | Quality | High | 2026-06-07 | 2026-06-07 | Verified | EV-002 | Inspection record and rework log reviewed | M. Rivera 2026-06-07 | Verified complete | No |  | Not due | 2026-06-07 | 12 parts reworked; no product shipped before inspection.
A3 | RCA-2026-014 | Operator could not easily see threadlocker requirement at pack station | NCR | Corrective action - occurrence cause | Occurrence root cause: work instruction lacked clear visual standard at point of use | Update WI-PACK-07 with photo standard showing required threadlocker location and acceptable coverage. | S. Chen | Manufacturing Engineering | High | 2026-06-14 | 2026-06-13 | Verified | EV-003 | Released work instruction checked against revision log | M. Rivera 2026-06-13 | Verified complete | Yes | 2026-07-13 | Monitoring continuing |  | Visual standard added; old revision removed from station.
A4 | RCA-2026-014 | Pack station did not prompt threadlocker check | NCR | Corrective action - occurrence cause | Occurrence root cause: no visual prompt or fixture cue at pack station | Add fixture flag and green visual prompt at pack station before part is released to packaging. | L. Brooks | Production | Medium | 2026-06-18 | 2026-06-17 | Verified | EV-004 | Station walk-through and photo evidence | M. Rivera 2026-06-17 | Verified complete | Yes | 2026-07-17 | Monitoring continuing |  | Prompt placed at operator eye level.
A5 | RCA-2026-014 | Final inspection did not catch missing threadlocker | NCR | Corrective action - escape / detection | Escape point: final inspection checklist did not include threadlocker presence | Revise final inspection checklist to include threadlocker presence and record lot-level sign-off. | K. Wilson | Quality | High | 2026-06-18 | 2026-06-18 | Effectiveness check pending | EV-005 | Checklist release and first completed inspection record | M. Rivera 2026-06-18 | Verified complete | Yes | 2026-07-18 | Monitoring continuing |  | Checklist changed before next production lot.
A6 | RCA-2026-014 | Same pack station standard may affect similar bracket families | NCR | Preventive action, if applicable | Potential similar process weakness on sister bracket family | Review sister bracket pack station and add the same visual prompt where the threadlocker step is used. | L. Brooks | Production | Medium | 2026-06-24 | 2026-06-24 | Verified | EV-006 | Station walk-through and photo evidence | M. Rivera 2026-06-24 | Verified complete | No |  | Not due | 2026-06-24 | No similar defect found, but visual prompt was added as a preventive control.
Example evidence log
Evidence ID | Related Action ID | Evidence type | What the evidence shows | File name / link / location | Owner | Date added | Reviewed by | Supports closure? | Notes
EV-001 | A1 | Photo | Quarantine tags applied to finished goods and WIP from Lot L0626. | Photos/CAP-2026-014/EV-001.jpg | J. Nguyen | 2026-06-05 | M. Rivera | Yes | Matches quarantine list.
EV-002 | A2 | Inspection result | 100% inspection completed; 12 parts reworked, 0 shipped before release. | Inspection Log IL-0626-Threadlocker.xlsx | A. Patel | 2026-06-07 | M. Rivera | Yes | Supports immediate correction.
EV-003 | A3 | Updated work instruction | WI-PACK-07 Rev D includes photo standard and point-of-use requirement. | WI-PACK-07 Rev D.pdf | S. Chen | 2026-06-13 | M. Rivera | Yes | Old revision removed.
EV-004 | A4 | Photo | Station walk-through confirms fixture flag placed at operator eye level. | Photos/CAP-2026-014/EV-004.jpg | L. Brooks | 2026-06-17 | M. Rivera | Yes | Station photo taken before and after.
EV-005 | A5 | Control plan / inspection plan | Final inspection checklist now includes threadlocker presence check. | QC-CHK-22 Rev B.pdf | K. Wilson | 2026-06-18 | M. Rivera | Yes | First completed checklist attached.
EV-006 | A6 | Photo | Sister bracket pack station visual prompt was added after review. | Photos/CAP-2026-014/EV-006.jpg | L. Brooks | 2026-06-24 | M. Rivera | Yes | Preventive check for similar process.
Example effectiveness check
Effectiveness Check ID | Related Action ID | Related issue / root cause | Check method | Lot / quantity sample size checked | Time window tracked | Production area / process reviewed | Acceptance criteria | Result | Evidence ID / link | Further action needed? | Decision owner | Decision date | Notes
EC-001 | A3/A4/A5 | Missing threadlocker caused by weak point-of-use instruction and missed final inspection | Review next 3 production lots and customer complaint log after 30 days. | 1,500 pieces across 3 lots | 2026-06-19 to 2026-07-18 | Pack station and final inspection | Zero missing threadlocker findings and no repeat complaint after 30 days. | Monitoring continuing | EV-003 / EV-004 / EV-005 | No | M. Rivera | 2026-07-18 | Do not close CAP until the 30-day complaint review is complete.
© 8Dflow.com For internal business use only. General manufacturing quality reference; adapt before use. No warranty is given as to accuracy, completeness, suitability, or compliance with any audit, regulatory, contractual, certification, or legal requirement. Do not redistribute, resell, or publish without 8Dflow’s written permission.

## Lists
Dropdown Lists [DO NOT MODIFY]
Action type | Issue Type | Status | Priority / risk | Verification result | Effectiveness required | Effectiveness result | Evidence type | Supports closure | Further action needed
Containment | NC | Not started | Low | Not checked | Yes | Not due | Photo | Yes | Yes
Immediate correction / product rework | OFI | In progress | Medium | Verified complete | No | Effective | Inspection result | No | No
Corrective action - occurrence cause | Customer complaint | Waiting on evidence | High | Partial / needs follow-up |  | Not effective | Test report | Needs review
Corrective action - escape / detection | NCR | Complete - pending verification | Customer-critical | Not accepted |  | Monitoring continuing | Work order / router
Preventive action, if applicable | SCAR | Verified |  |  |  | More data needed | Updated work instruction
| 8D | Effectiveness check pending |  |  |  |  | Training record
| Internal finding | Closed |  |  |  |  | Maintenance record
| Supplier issue | Overdue |  |  |  |  | Machine setting / setup sheet
| Other | [5 empty] | Control plan / inspection plan
Drawing / specification
Customer email
Supplier response
Other
© 8Dflow.com For internal business use only. General manufacturing quality reference; adapt before use. No warranty is given as to accuracy, completeness, suitability, or compliance with any audit, regulatory, contractual, certification, or legal requirement. Do not redistribute, resell, or publish without 8Dflow’s written permission.